## Sheet1
EXHIBIT PLANNING CHECKLIST & TIMELINE
| Person | Deadline | Date
| Responsible | Date | Completed
Show Selection
Verify target market; consider current customer profile to compare to attendee demographics | ________ | ________ | ________
Research shows (audited attendee and exhibitor demographics, show history and growth, exhibitor references) | ________ | ________ | ________
Determine size of booth space required based on number of target audience at show and products to show them
Select booth space and sign space contract; wait list for better space if not satisfied with available spaces
Complete accounting paperwork to make deposit and ongoing payment(s) | ________ | ________ | ________
Receive confirmation from Show Management of space contracted and payment receipt | ________ | ________ | ________
Assemble your Trade Show Team (Stakeholders)
Select your internal team (marketing, sales, product engineering, facilities, shipping, etc.) | ________ | ________ | ________
Select your external team (exhibit/graphics house, transportation carrier, PR, advertising and social media agency) | ________ | ________ | ________
Pre-Show Strategy and Supporting Tactics
Set meeting to determine exhibit strategy and key messaging | ________ | ________ | ________
Set realistic written goals and objectives for Return on Investment/Objective/Relationship | ________ | ________ | ________
ROI: Sales leads/sales/revenue/profit | ________ | ________ | ________
ROO: Corporate branding/awareness | ________ | ________ | ________
ROO: Media/press interaction and at-show/post-show mentions in targeted press | ________ | ________ | ________
ROO: Audience education on new products/technology/improvements | ________ | ________ | ________
ROR: Relationship-building with current customers/clients to facilitate resales/upsales | ________ | ________ | ________
Create dynamic timeline of internal and external deadlines | ________ | ________ | ________
Determine presentation/demos | ________ | ________ | ________
Set show budget (See Budget Worksheet template) | ________ | ________ | ________
Determine exhibit staffing requirements and select appropriate, motivated staff | ________ | ________ | ________
Notify exhibit staff of selection, show dates, when airline tickets should be purchased; pre-show meeting time | ________ | ________ | ________
Receive Official Exhibitor Services Manual: | ________ | ________ | ________
Read and review entire Exhibitor Services Manual, including rules/regulations | ________ | ________ | ________
Mark all forms requiring completion; highlight deadlines and update timeline | ________ | ________ | ________
Order show services prior to discount deadlines and make payments | ________ | ________ | ________
Exhibit
Determine, inventory and/or produce:
exhibit properties (towers, walls, kiosks, tables, lighting, carpet/pad, etc.) | ________ | ________ | ________
graphics/signage (copy and background art) | ________ | ________ | ________
products or equipment | ________ | ________ | ________
computer or AV equipment for demonstrations | ________ | ________ | ________
supplies | ________ | ________ | ________
Promotion
Plan pre-show, at-show and post-show promotional strategies to contact current customers, prospects and suspects | ________ | ________ | ________
Evaluate all marketing promotional opportunities based on show goals (i.e. advertising, direct mail, sponsorships,
social media, banners, bus signage, hotel door hangers, show guide belly-bands, giveaways, events) | ________ | ________ | ________
Determine exhibit staff's booth uniform, request staff sizes and order logo'd items | ________ | ________ | ________
Order free exhibit hall passes for promotional distribution | ________ | ________ | ________
Submit exhibitor profile for conference program highlighting new products and product benefits | ________ | ________ | ________
Submit new product announcements for show management promotions | ________ | ________ | ________
Request press list, if available, and contact name for at-show press contact | ________ | ________ | ________
Finalize press releases and plan press briefing, if applicable | ________ | ________ | ________
Integrate pre-show, at-show and post-show promotional strategy with tactical timeline | ________ | ________ | ________
Lead Handling and Collaterals | ________ | ________ | ________
Determine qualifying information to be obtained from attendees and recorded on lead form | ________ | ________ | ________
Determine and/or produce collateral information to be distributed at show or from company Web site landing page | ________ | ________ | ________
Rent or purchase lead retrieval system with custom questions or print hard copy customized lead forms | ________ | ________ | ________
Finalize post-show lead fulfillment plan (email, direct mail postcard, brochure, sample, etc.) | ________ | ________ | ________
Determine after-fulfillment follow-up (database management, appointment setting, etc.) | ________ | ________ | ________
| Person | Deadline | Date
| Responsible | Date | Completed
Staffing
Communicate strategy, show dates, staff schedule, attire, and training information with show staff and vendors | ________ | ________ | ________
Order staff, partner and vendor badges | ________ | ________ | ________
Submit name for free conference registration (if available) | ________ | ________ | ________
Make hotel reservations through official housing block or corporate travel department | ________ | ________ | ________
Make air/ground travel arrangements | ________ | ________ | ________
Plan location and content (exhibit orientation/sales/etiquette) of pre-show staff training session | ________ | ________ | ________
Notify staff of pre-show training schedule | ________ | ________ | ________
Shipping
Determine shipping inventory with item count, dimensions and weight | ________ | ______ | ________
Determine if shipment will be sent to General Service Contractor's advance warehouse or direct-to-site | ________ | ______ | ________
Determine mode of transportation (common carrier, van line, air freight, small-package carrier, or company/personal
vehicle) | ________ | ______ | ________
Request shipping quotes from carriers, evaluate quotes and award contract to shipper | ________ | ______ | ________
Finalize shipping information with carrier, exhibit house, corporate warehouse to/from show | ________ | ______ | ________
Get/print shipping labels color code for shipments (to and from show site) and inbound/outbound bills of lading | ________ | ______ | ________
I & D
Select Installation & Dismantle (I & D) contractor (General Services Contractor or Exhibitor-Appointed Contractor) | ________ | ______ | ________
Complete EAC Forms to notify Show Management if using exhibitor-appointed contractor (EAC) | ________ | ______ | ________
Confirm that EAC has completed all required insurance documentation and payments | ________ | ______ | ________
Plan exhibit setup/dismantle schedule/requirements with exhibit house and I & D contractor | ________ | ______ | ________
Order On-Site Services
Review Exhibitor Services Manual for discount deadlines and add to deadline list | ________ | ______ | ________
Complete forms and submit to proper vendors | ________ | ______ | ________
Update budget with semi-final amounts from on-site services forms | ________ | ______ | ________
At-Show
Pick up badges at exhibitor registration (if receiving all staff badges) | ________ | ______ | ________
Pick up complimentary conference pass (if provided) | ________ | ______ | ________
Check status of freight delivery and under-carpet electrical/Internet/cable installation | ________ | ______ | ________
Confirm on-site services at respective contractors' Service Desks | ________ | ______ | ________
Confirm inbound shipment inventory/weights at General Services Contractor's Service Desk | ________ | ______ | ________
Supervise exhibit and equipment installation | ________ | ______ | ________
Deliver press kits to official show press room | ________ | ______ | ________
Confirm with Show Management date/time for on-site booth space selection | ________ | ______ | ________
Pick up rented lead retrieval system | ________ | ______ | ________
Provide in-booth orientation and offsite staff boothmanship/sales training | ________ | ______ | ________
Hold meetings with exhibit staff at end of each shift; make changes/improvements based on their feedback | ________ | ______ | ________
Audit General Services Contractor, subcontractor and facility utility invoices for accuracy | ________ | ______ | ________
Reconfirm outbound services (dismantle, rigging, shipping, etc.) | ________ | ______ | ________
Pick up outbound Uniform Material Handling Agreement from General Services Contractor's Service Desk | ________ | ______ | ________
At Show Close
Return lead retrieval system and secure leads (online password/thumb drive/CD, etc.) | ________ | ______ | ________
Return rented show equipment i.e. Internet, phone equipment, etc. | ________ | ______ | ________
Pack product, equipment, collateral, giveaways, supplies, etc. | ________ | ______ | ________
Supervise dismantle of hanging signs, exhibit and graphics | ________ | ______ | ________
Supervise repacking of all exhibit properties and label for outbound shipment | ________ | ______ | ________
Complete your carrier's Bill of Lading and General Service Contractor's Uniform Material Handling Agreement | ________ | ______ | ________
Turn in Bill(s) of Lading and Material Handling Agreement at General Services Contractor's Service or Freight Desk
before leaving convention facility; get copy with date/time turned in and sign by GSC representative | ________ | ______ | ________
Post-Show
Submit personal expense report | ________ | ______ | ________
Fulfill show inquiries/requests | ________ | ______ | ________
Write thank-you notes to booth staffers, vendors, show staff | ________ | ______ | ________
Distribute Post-Show Staff Surveys; follow-up; compile results | ________ | ______ | ________
Audit final invoices/pay final invoices/finalize show budget | ________ | ______ | ________
Measure/analyze results (ROI/ROO/ROR) | ________ | ______ | ________
Hold post-show team meeting to share results and solicit improvement-based feedback | ________ | ______ | ________
Compose Post-Show Analysis Report and Executive Brief and distribute to stakeholders/execs | ________ | ______ | ________
Copyrighted to Candy Adams, "The Booth Mom®", Trade Show Consulting,© Vista, CA 2018